## Summary
Translation Review — Outstanding Work (as of this release, 2026-10-13)
THE SINGLE MOST IMPORTANT FACT: 0% of translation content in this application has been reviewed by a native speaker or qualified medical translator -- across all 36 languages, all 96 questions, all 3,456 cells. This file lists the highest-priority items first; it does not mean everything else is "fine" -- it has simply not surfaced a specific concern in an AI read, which is not the same as a human clearance.
Sheet 1 -- Priority Action Items: the 8 concrete findings from the full translation audit, ranked with the one already applied to the live app (Tamil NEURO03) first, since it most urgently needs independent confirmation now that patients may see the corrected text.
Sheet 2 -- Lower-Confidence Languages: 15 languages the AI reviewer flags as warranting earlier/closer native-speaker attention even where no specific issue was found in them.
Total findings requiring action: 8
Already applied to the live app (still needs confirmation): 1
Proposed only, not yet applied: 7
Lower-confidence-tier languages flagged for priority review: 15 of 36
For the full 3,456-cell matrix (every question in every language, with its review status), see Translation_Clinical_Language_Review.xlsx. This file is a prioritised subset of that matrix for a reviewer deciding where to start, not a replacement for it.

## Priority Action Items
Priority | Question ID | Language | Language Code | English Master Question | Current Live Translation | Suggested Translation | Alternate Suggestion (if any) | Why This Needs Review | Category | Severity | Confidence | Status in This Release
1 | NEURO03 | Tamil | ta | Was it the worst headache you have ever had? | இது இதுவரை நீங்கள் அனுபவித்ததிலேயே மிக மோசமான தலைவலியா? | இது இதுவரை நீங்கள் அனுபவித்ததிலேயே மிக மோசமான தலைவலியா? |  | CONFIRMED (upgraded from medium to high confidence after a full morphological decomposition, done at the project owner's explicit request to prioritise this item). Word-by-word: 'இது' (this) 'நீங்கள்' (you) 'என்றுமே' (ever) 'அனுபவிக்காத' (that-has-not-been-experienced) 'மோசமான' (bad) 'தலைவலியா' (is-it-a-headache). The suffix '-க்காத' in 'அனுபவிக்காத' is Tamil's standard negative relative-participle marker (the same productive pattern as, e.g., 'படிக்காத பையன்' = 'the boy who has NOT studied') -- it is not a typo or an ambiguous construction, it is the regular, textbook way Tamil forms 'has not done X'. So the existing sentence reads literally as 'Is this the worst headache that you have NEVER experienced?' -- the exact opposite of the intended 'the worst headache you have EVER had'. No other instance of this suffix pattern exists elsewhere in the Tamil file to serve as an internal cross-check, so this finding rests on direct grammatical analysis rather than in-file precedent -- hence still recommending native-speaker confirmation despite the high confidence, consistent with 'keep all changes marked as unverified until independently checked.' Suggested correction replaces the negative participle with the correct affirmative construction: 'இதுவரை...அனுபவித்ததிலேயே' ('among all you have experienced so far'), restoring the intended superlative-'ever' meaning without changing anything else about the question. NEURO03 is this project's own worked red-flag example (thunderclap/SAH headache screening) and the highest-stakes single question in the General/Neuro cluster -- this remains the single highest-priority item for native-speaker/qualified-translator confirmation in this entire audit. | major_translation_error | high | high | APPLIED to the live translation file on 2026-10-13 as a development-release change -- STILL UNVERIFIED, requires independent native-speaker confirmation before being treated as correct.
2 | CVS05 | Russian | ru | Have you fainted? | Вы теряли сознание? | Вы падали в обморок? | У вас был обморок? | Russian CVS05 is worded identically to NEURO11 and TRAUMA05 (both 'Вы теряли сознание?' -- same verb phrase, 'to lose consciousness'). Russian has a distinct, common everyday word for fainting/syncope -- обморок -- which every other reviewed language in this project (Ukrainian, Spanish, French, Arabic, Farsi, German, Italian, etc.) uses to keep this exact 3-way clinical distinction the English source and the brief's own worked example (CVS05 / NEURO11 / TRAUMA05) explicitly calls for. As written, a Russian-speaking patient's answer to CVS05 cannot be clinically distinguished from their answer to NEURO11 or TRAUMA05. REVISED for natural, patient-friendly phrasing per the project owner's request: 'Вы падали в обморок?' (literally 'did you fall into a faint', the standard everyday spoken way to ask this in Russian -- noticeably more conversational than the flatter noun-phrase alternative 'У вас был обморок?' ('did you have a fainting episode'), which is kept as `suggested_alt` since it is also correct and slightly more formal/clinical in register. Either keeps the CVS05/NEURO11/TRAUMA05 distinction intact; the project owner or a native speaker may prefer one register over the other. | clinical_meaning_concern | high | high | NOT applied -- proposal only, awaiting native-speaker/qualified-translator review.
3 | CVS05 | Hindi | hi | Have you fainted? | क्या आप बेहोश हुए हैं? | क्या आपको गश आया है? | क्या आपको मूर्छा आई है? | Hindi CVS05, NEURO11 and TRAUMA05 are all worded identically ('क्या आप बेहोश हुए हैं?' -- 'have you become unconscious?'). REVISED for natural, patient-friendly phrasing per the project owner's request: 'क्या आपको गश आया है?' uses गश (gash), a widely understood colloquial Hindi-Urdu-belt term for a fainting spell commonly used in everyday speech (as in 'गश खाकर गिर पड़ा', 'fainted and fell') -- this reads more naturally to an ordinary patient, including one with limited health literacy, than the more Sanskritised/literary मूर्छा ('moorchha'), which is kept as `suggested_alt` since it is the more formal/standard-register alternative and may be preferred in some registers or regions. Either word is lexically distinct from बेहोश (NEURO11/TRAUMA05's 'unconscious'), so either restores the clinical distinction. Flagged medium rather than high confidence because Hindi colloquial-register conventions, and which of गश/मूर्छा reads best across different Hindi-speaking regions, should be confirmed by a native speaker/qualified medical translator before changing. | clinical_meaning_concern | high | medium | NOT applied -- proposal only, awaiting native-speaker/qualified-translator review.
4 | CVS05 | Urdu | ur | Have you fainted? | کیا آپ بیہوش ہو گئے ہیں؟ | (none proposed -- flagged for qualified review) |  | Urdu CVS05 ('بیہوش ہو گئے ہیں') and NEURO11/TRAUMA05 ('بے ہوش ہوئے ہیں') share the same root word for 'unconscious' (بے ہوش / بیہوش -- a spacing variant of the same word) with only the surrounding verb construction differing. This may or may not read as a meaningful clinical distinction to an Urdu-speaking patient -- the AI reviewer does not have high enough confidence in Urdu medical-register conventions to say definitively either way, so this is flagged for qualified review rather than marked as either correct or incorrect. | requires_native_speaker_review | medium | low | NOT applied -- proposal only, awaiting native-speaker/qualified-translator review.
5 | GI03/GI04/TRAUMA06 | Tigrinya | ti | Have you vomited? / Have you vomited blood? / Have you vomited since the injury? | GI03: 'ተመሊስካ (ትምዒ) ድዩ?' ¦ GI04: 'ብደም ተመሊስካ ድዩ?' ¦ TRAUMA06: 'ድሕሪ እቲ ጉድኣት ተመሊስካ ድዩ?' | (none proposed -- flagged for qualified review) |  | The verb used for 'vomited' across these three questions is ተመሊስካ, which literally means 'returned'/'came back'. Tellingly, the translator's OWN GI03 entry adds a parenthetical clarifying gloss '(ትምዒ)' next to it -- suggesting the base verb alone was felt to be ambiguous enough to need clarification -- but that same clarifying gloss was not carried over to GI04 or TRAUMA06, which use ተመሊስካ alone. This is an internal-consistency flag, not a confirmed mistranslation (Tigrinya is one of the two lowest-confidence languages in this project, alongside Kurdish Kurmanji, per the standing QA-report guidance) -- recommend a native speaker confirm whether ተመሊስካ alone is unambiguous for 'vomited' in natural spoken Tigrinya, and if not, add the '(ትምዒ)' clarifier consistently to GI04 and TRAUMA06 as well as GI02/GI03. | requires_native_speaker_review | medium | low | NOT applied -- proposal only, awaiting native-speaker/qualified-translator review.
6 | CVS05 | Malayalam | ml | Have you fainted? | ബോധക്ഷയം ഉണ്ടായോ? | (none proposed -- flagged for qualified review) |  | Malayalam CVS05 ('ബോധക്ഷയം', a compound built on the same root -- ബോധം, 'consciousness' -- as NEURO11's 'ബോധം നഷ്ടപ്പെട്ടോ') is a different, more specific compound word than NEURO11/TRAUMA05's phrasing, so a clinical distinction may already be intact -- but the AI reviewer's confidence in Malayalam is too low to confirm this without a native speaker. | requires_native_speaker_review | low | low | NOT applied -- proposal only, awaiting native-speaker/qualified-translator review.
7 | CVS05 | Gujarati | gu | Have you fainted? | શું તમે બેભાન થયા છો? | (none proposed -- flagged for qualified review) |  | Gujarati CVS05 ('બેભાન થયા છો') and NEURO11/TRAUMA05 ('ભાન ગુમાવ્યું છે') share the root ભાન ('consciousness') with a different grammatical construction. As with Malayalam, a distinction may already be intact in natural usage, but this is outside the AI reviewer's confident range for Gujarati -- flagged for qualified review. | requires_native_speaker_review | low | low | NOT applied -- proposal only, awaiting native-speaker/qualified-translator review.
8 | CVS06 | Latvian | lv | Have you had difficulty breathing when lying flat? | Vai bija grūti elpot, guļot uz muguras? | (none proposed -- flagged for qualified review) |  | 'guļot uz muguras' translates as 'lying on your back' specifically, rather than 'lying flat' more generally (which could include lying on one's side). For orthopnoea screening this is very unlikely to change a patient's actual answer in practice (lying flat in a bed overwhelmingly means lying on one's back), so this is a low-severity wording note rather than a clinical concern, flagged for a native speaker to confirm it doesn't narrow the question in practice. | minor_language_improvement | low | medium | NOT applied -- proposal only, awaiting native-speaker/qualified-translator review.

## Lower-Confidence Languages
Language Code | Reason flagged | Recommended priority
am (Amharic) | Flagged as a lower-resourced language for the underlying AI model; a clean AI read here carries less confidence than for a higher-resource language, even where no specific issue was found. | Medium-high
bg (Bulgarian) | Flagged as a lower-resourced language for the underlying AI model; a clean AI read here carries less confidence than for a higher-resource language, even where no specific issue was found. | Medium-high
gu (Gujarati) | Flagged as a lower-resourced language for the underlying AI model; a clean AI read here carries less confidence than for a higher-resource language, even where no specific issue was found. | Medium-high
ka (Georgian) | Flagged as a lower-resourced language for the underlying AI model; a clean AI read here carries less confidence than for a higher-resource language, even where no specific issue was found. | Medium-high
kmr (Kurdish (Kurmanji)) | Flagged as a lower-resourced language for the underlying AI model; a clean AI read here carries less confidence than for a higher-resource language, even where no specific issue was found. | Medium-high
ku (Kurdish (Sorani)) | Flagged as a lower-resourced language for the underlying AI model; a clean AI read here carries less confidence than for a higher-resource language, even where no specific issue was found. | Medium-high
lt (Lithuanian) | Flagged as a lower-resourced language for the underlying AI model; a clean AI read here carries less confidence than for a higher-resource language, even where no specific issue was found. | Medium-high
lv (Latvian) | Flagged as a lower-resourced language for the underlying AI model; a clean AI read here carries less confidence than for a higher-resource language, even where no specific issue was found. | Medium-high
ml (Malayalam) | Flagged as a lower-resourced language for the underlying AI model; a clean AI read here carries less confidence than for a higher-resource language, even where no specific issue was found. | Medium-high
pa (Punjabi) | Flagged as a lower-resourced language for the underlying AI model; a clean AI read here carries less confidence than for a higher-resource language, even where no specific issue was found. | Medium-high
ps (Pashto) | Flagged as a lower-resourced language for the underlying AI model; a clean AI read here carries less confidence than for a higher-resource language, even where no specific issue was found. | Medium-high
so (Somali) | Flagged as a lower-resourced language for the underlying AI model; a clean AI read here carries less confidence than for a higher-resource language, even where no specific issue was found. | Medium-high
ta (Tamil) | Flagged as a lower-resourced language for the underlying AI model; a clean AI read here carries less confidence than for a higher-resource language, even where no specific issue was found. Contains the confirmed, applied NEURO03 correction -- highest priority of this whole list. | High
ti (Tigrinya) | Flagged as a lower-resourced language for the underlying AI model; a clean AI read here carries less confidence than for a higher-resource language, even where no specific issue was found. | Medium-high
yue-Hant (Cantonese (Traditional)) | Flagged as a lower-resourced language for the underlying AI model; a clean AI read here carries less confidence than for a higher-resource language, even where no specific issue was found. | Medium-high